## Sheet1
Related User Story | Task Description | Initial Estimate | Assigned To | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3
Rank | Edit lib page to display rank | 2 | Nate | 0 | 1 | 0
| Edit add page to add rank | 2 | Chris | 0 | 1 | 0
| Edit Library of songs to store rank | 2 | Trinidad | 0 | 1 | 0
Tags | Edit library of songs to store tags | 2 | Nate | 2 | 2 | 0
| Edit library page to display tags | 2 |  | 2 | 2 | 0
| Edit add page to add tags (can't add duplicate tags, autocomplete tags) | 3 |  | 3 | 2 | 0
| Integrate error handling/messaging for missing required information | 3 |  | 3 | 2 | 0
| Integrate valididation for information entered/missing | 2 |  | 2 | 2 | 0
Edit | Update song in the system, whether it is complete or not | 2 | Chris | 2 | 2 | 0
| Edit song via edit option button in UI | 2 |  | 2 | 2 | 0
| Confirmation dialog for information entered is presented | 2 |  | 2 | 2 | 0
| Integrate validation for information entered/missing | 3 |  | 3 | 2 | 0
| Integrate error handling/messaging for missing required information | 3 |  | 3 | 2 | 0
Generate Playlist | Provide seed information with target playlist length and some ranked songs | 2 | Trinidad | 2 | 1 | 0
| Generates playlist with no repeated songs | 5 |  | 5 | 3 | 0
| If no length, generate 10-15 songs | 3 |  | 3 | 2 | 0
| If no rank or seed, generate playlist based on available information | 2 |  | 2 | 1 | 0
| If no info provided, generate 10-15 songs based on available information | 2 |  | 2 | 1 | 0
*Refer to Documentation for context*
| Estimate Totals | 44 |  | 38 | 31 | 0
Requirements.pdf
Product Backlog.xlsx
PlayList Generator - Use Case Scenarios.pdf
high-quality-professionally-developed-ui-design.jpg